PLAN

We planned to implement three high priority big user stories for Iteration 1 which were:

1) Note taking and saving them

Expected Delivery time: 6 Days

2) Add image from gallery or using camera and add it to my notes

Expected Delivery time: 5 Days

3) Draw something on screen and add it to notes

Expected Delivery time: 6 Days

Since we almost finished what we planned, we are going to stick to our original plan and finish the following three features for the next iteration. Also, we will be replacing the stub database with the actual SQLite database.

For iteration 2, we plan to complete the following features:

1) View PDFs: view and open an existing PDF file

Expected Delivery time: 5 days

2) Modify Notes: Able to edit and delete notes, open the saved the notes

Expected Delivery time: 5 days

3) Modify PDFs: write my own notes to the PDF files and highlight the content of the PDF files

Expected Delivery time: 7 days

---------------------------------

Planning part for iteration 2

we were able to finish most parts for the this iteration

changes -> use of adobe to open the PDF's, and also the checklist was supposed to be implemented for iteration 3 , but it was implemented in this iteration

For the next iteration we will be doing the following features

- add calendar and reminder

- save checklist to DB

-proper implementation and modification of PDF's

-------------------------------------------------------------

**Plan for iteration 3**

Changes-> After considering cost and other such issues, we spoke with our Client and agreed upon using third party applications for PDF viewer (Adobe Reader) and for Calendar and Reminder (Google calendars) feature. Also, the calendar and reminder features were merged together as customer felt it was more useful and he requested for it specifically later. These changes brought the cost down by quite much. The combined cost of calendar and reminder feature was 12 days(7+5) which was brought down to 5 days with the use of third party default Calendar application. Also, the cost of Pdf feature was brought down from 12 days (view 5+modify 7) to 4 days with the use of third party adobe reader app as agreed upon by the customer who felt it was more useful and logical. Although we saved quite much time on these two features, we had to spend majority of that time implementing the SQLite database and the Listview features. Their actual cost was much more than what we had initially expected.

**Issue:**

The Do-Not-Disturb feature just sets the device to silent mode until changed back to ringer mode manually in the app. It doesn't set it off automatically after a specified time as that part of the feature could not be implemented due to time constraints but we discussed it with our client, and explained our situation after which he had no quarrels with it. Rest all the features were implemented to completion.